## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Light
CSC3003S Capstone Project
| University of Cape Town |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
| Project Start Date: | 2022-08-01 |  |  |  |  | August | [34 empty] | September
| Scrolling Increment: | 1 | time axis 2022-08-02 to 2022-09-26
| Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2022-08-02 to 2022-09-26
Stage 1
| Scope |  | Erin, Ben | 100% | 2022-08-01 | 5
| Risk |  | Zenan | 100% | 2022-08-01 | 5
| Role |  | Erin, Ben, Zenan | 100% | 2022-08-01 | 5
Stage 2
| Progress report, Interation Diagram |  | Erin | 50% | 2022-08-06 | 7
| Use case description, Analysis Class Model |  | Ben | 50% | 2022-08-06 | 7
| Project Plan, Preliminary Test Plan |  | Zenan | 50% | 2022-08-06 | 7
| Progress check | Milestone |  |  | 2022-08-10 | 1 | bar: 2022-08-10
Stage 3
| Progress report |  |  | 0% | 2022-08-13 | 7
| Marking Evolutionary Prototype |  |  | 0% | 2022-08-13 | 7
| Marking Throw-Away Prototype |  |  | 0% | 2022-08-13 | 7
| Progress check | Milestone |  |  | 2022-08-17 | 1 | bar: 2022-08-17
| Demonstration to Client and Tutor | Milestone |  |  | 2022-08-19 | 1 | bar: 2022-08-19
Stage 4
| Read and write and organize data from PDF to a notepad | Goal |  | 5% | 2022-08-06 | 14 | 2022-08-06: 2; 2022-08-07: 2; 2022-08-08: 2; 2022-08-09: 2; 2022-08-10: 2; 2022-08-11: 2; 2022-08-12: 2; 2022-08-13: 2; 2022-08-14: 2; 2022-08-15: 2; 2022-08-16: 2; 2022-08-17: 2; 2022-08-18: 2; 2022-08-19: 2
| Read and write data from notepad to Access | Goal |  | 0% | 2022-08-20 | 7 | 2022-08-20: 2; 2022-08-21: 2; 2022-08-22: 2; 2022-08-23: 2; 2022-08-24: 2; 2022-08-25: 2; 2022-08-26: 2
| Creating a website, structure the inputs and outputs | Goal |  | 0% | 2022-08-20 | 7 | 2022-08-20: 2; 2022-08-21: 2; 2022-08-22: 2; 2022-08-23: 2; 2022-08-24: 2; 2022-08-25: 2; 2022-08-26: 2
| Progress Check | Milestone |  |  | 2022-08-24 | 1 | bar: 2022-08-24
| Progress Check | Milestone |  |  | 2022-08-31 | 1 | bar: 2022-08-31
| Search the all routes with the inputs from the user | Goal |  | 0% | 2022-08-27 | 7 | 2022-08-27: 2; 2022-08-28: 2; 2022-08-29: 2; 2022-08-30: 2; 2022-08-31: 2; 2022-09-01: 2; 2022-09-02: 2
| Progress Check | Milestone |  | 0% | 2022-09-07 | 1 | bar: 2022-09-07
| User login, save search results, Using Access?? | Goal |  | 0% | 2022-09-03 | 7 | 2022-09-03: 2; 2022-09-04: 2; 2022-09-05: 2; 2022-09-06: 2; 2022-09-07: 2; 2022-09-08: 2; 2022-09-09: 2
| Find the earliest possible arrival time | Med Risk |  | 0% | 2022-08-30 | 12
| Autocomplete functionality for typing in the train station | Med Risk |  | 0% | 2022-08-30 | 12
| Progress Check | Milestone |  |  | 2022-09-14 | 1 | bar: 2022-09-14
| Putting all the codes together and testing. | Goal |  | 0% | 2022-09-10 | 7 | 2022-09-10: 2; 2022-09-11: 2; 2022-09-12: 2; 2022-09-13: 2; 2022-09-14: 2; 2022-09-15: 2; 2022-09-16: 2
| Progress Check | Milestone |  |  | 2022-09-21 | 1 | bar: 2022-09-21
v | Final Report | Goal |  | 0% | 2022-09-17 | 7 | 2022-09-17: 2; 2022-09-18: 2; 2022-09-19: 2; 2022-09-20: 2; 2022-09-21: 2; 2022-09-22: 2; 2022-09-23: 2
| Handin | Goal |  |  | 2022-09-23 | 1 | 2022-09-23: 2

## Color
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2022-08-11 |  |  |  |  | August | [20 empty] | September | [27 empty] | October
Scrolling Increment: | 5 | time axis 2022-08-16 to 2022-10-10
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2022-08-16 to 2022-10-10
Stage 1
Scope | Goal | Zenan, Erin, Ben | 100% | 2022-08-04 | 5
Risk | Milestone |  |  | 2022-08-16 | 1 | bar: 2022-08-16
Role | Low Risk |  | 50% | 2022-08-01 | 10
Task 4 | Milestone |  |  | 2022-08-24
Task 5 | Med Risk |  | 10% | 2022-08-10 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2022-08-10 | 13
Task 2 | On Track |  | 50% | 2022-08-12 | 9
Task 3 | Low Risk |  | 33% | 2022-08-17 | 11
Task 4 | Milestone |  |  | 2022-08-19 | 1 | bar: 2022-08-19
Task 5 |  |  |  | 2022-08-20 | 24
TITLE 3
Task 1 | On Track |  |  | 2022-08-19 | 4
Task 2 | Med Risk |  |  | 2022-08-22 | 14
Task 3 | On Track |  |  | 2022-09-06 | 6
Task 4 | Goal |  |  | 2022-09-10 | 3 | 2022-09-10: 2; 2022-09-11: 2; 2022-09-12: 2
Task 5 | Low Risk |  |  | 2022-08-10 | 19
TITLE 4
Task 1 |  |  |  | 2022-09-13 | 15
Task 2 |  |  |  | 2022-09-27 | 5
Task 3 | Milestone |  |  | 2022-11-08 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one